# KYCSHIELD BY FACTI.AI

## 20-Day Development Timeline to Investor Demo

Target: First Week of December 2025

Goal: Production-ready MVP for fundraising

# EXECUTIVE SUMMARY

KYCShield is a cybersecurity middleware that detects AI-powered fraud in KYC verification systems. While traditional KYC checks if someone is real, KYCShield checks if the media itself is real - catching ProKYC and similar deepfake tools that bypass standard identity verification.

Timeline: 20 days

Total Investment: $81

Deliverables:

Working video deepfake detector (95%+ accuracy)

Working synthetic ID detector (95%+ accuracy)

Cross-artifact correlation engine

Live demo for investors

Integration with Trusi consumer app

# WEEK 1: VIDEO DEEPFAKE DETECTION

## November 20-26, 2025

### Objective

Train and deploy a video deepfake detector that identifies AI-generated faces in liveness verification videos. This detector will power both KYCShield (B2B) and Trusi (B2C).

### Tasks

Day 1-2: Dataset Acquisition

• Download FaceForensics++ dataset (1,000 real + 4,000 fake videos)

• Download Celeb-DF dataset (5,639 deepfake videos)

• Organize and label training data

• Set up Lambda Labs GPU account

Day 3-5: Model Training

• Train 3D CNN architecture on video data

• Target: 95%+ accuracy on test set

• Optimize for < 1 second inference time

• Monitor training progress and adjust hyperparameters

Day 6-7: Deployment & Testing

• Deploy model to KYCShield API

• Integrate with Trusi mobile app

• Test with real-world videos

• Measure accuracy and speed

### Detection Capabilities

Frame pacing irregularities

Lip-sync timing issues

GAN fingerprints in facial features

Smoothed skin patterns

Uniform color patches

Abnormal eye reflections

Temporal stability anomalies

### Success Metrics

Accuracy: ≥ 95%

False Positive Rate: < 1%

Inference Speed: < 1 second

Works on both products: KYCShield + Trusi

### Investment

Cost: $54

Lambda Labs GPU rental for training (48-72 hours)

### Milestone

✓ Video deepfake attacks blocked in real-time

# WEEK 2: SYNTHETIC ID DETECTION

## November 27 - December 3, 2025

### Objective

Train and deploy a synthetic ID detector that identifies AI-generated identity documents. This component is exclusive to KYCShield and addresses the document forgery vector.

### Tasks

Day 1-2: Dataset Acquisition

• Collect real ID document datasets (MIDV-500, academic sources)

• Generate synthetic ID samples using GAN/diffusion models

• Create balanced training set (10,000 real + 10,000 fake)

• Label and organize data

Day 3-5: Model Training

• Train ResNet-50 on ID documents

• Target: 95%+ accuracy on test set

• Optimize for < 5 second inference time

• Fine-tune detection thresholds

Day 6-7: Integration & Demo Build

• Deploy model to KYCShield API

• Create basic frontend demo interface

• Test with sample ProKYC-style attacks

• Begin demo video recording

### Detection Capabilities

GAN artifacts in ID photos

Missing sensor noise patterns

Font spacing errors

Missing microprint patterns

Unrealistic shadows and lighting

Blank or reset metadata fields

Absence of lens distortion

Perfect color uniformity (synthetic signature)

### Success Metrics

Accuracy: ≥ 95%

False Positive Rate: < 1%

Inference Speed: < 5 seconds

Detects multiple ID types (passport, driver license, etc.)

### Investment

Cost: $27

Lambda Labs GPU rental for training (12-18 hours)

### Milestone

✓ Synthetic ID documents detected with 95%+ accuracy

# WEEK 3: CROSS-ARTIFACT CORRELATION & POLISH

## December 4-10, 2025

### Objective

Build cross-artifact correlation engine, optimize performance, and create polished demos for investor presentations.

### Tasks

Day 1-2: Cross-Artifact Analysis

• Extract GAN fingerprints from video and ID

• Build correlation algorithm

• Detect when multiple artifacts share same AI signature

• Identify "impossibly perfect" matches

Day 3-4: Performance Optimization

• Optimize inference speed (target < 1 sec total)

• Reduce false positive rate

• Load testing and stress testing

• Memory optimization

Day 5-7: Demo Preparation

• Build KYCShield frontend demo interface

• Polish Trusi video deepfake feature

• Create demo videos showing attack detection

• Prepare side-by-side comparisons

• Record investor demo walkthrough

### Cross-Artifact Correlation Features

GAN signature matching across ID photo and video

Statistical noise pattern correlation

Shared generation timestamp detection

Detection of "too perfect" biometric alignment

Multi-modal consistency scoring

### Demo Deliverables

KYCShield live demo interface

Trusi mobile app with video detection

ProKYC attack demonstration video

Side-by-side comparison: Traditional KYC vs KYCShield

Recorded demo walkthrough for pitch

### Investment

Cost: $0

Algorithm development and optimization (no training needed)

### Milestone

✓ Complete fraud detection system with polished demo

# WEEK 4: INVESTOR READINESS

## December 11-17, 2025

### Objective

Final testing, create pitch materials, and prepare for investor meetings in first week of December.

### Tasks

Day 1-2: End-to-End Testing

• Test complete KYC flow with various attack scenarios

• Verify all components working together

• Edge case testing

• Performance benchmarking

Day 3-4: Sales Materials

• Pitch deck creation

• ROI calculator for banks

• Integration guide (2-week deployment)

• Technical architecture documentation

• Threat intelligence brief on ProKYC

Day 5-7: Presentation Practice

• Rehearse investor pitch

• Practice live demo

• Prepare Q&A responses

• Refine messaging and positioning

### Pitch Materials Deliverables

Investor pitch deck (15 slides)

Live demo script

ROI calculator spreadsheet

2-week integration timeline document

ProKYC threat intelligence brief

Technical architecture diagram

Competitive analysis

### Investment

Cost: $0

Documentation and materials creation

### Milestone

✓ Ready for investor meetings - First week of December

# PROJECT SUMMARY

## Total Investment

| Component | Cost | Timeline |
| --- | --- | --- |
| Video Deepfake Detection | $54 | Week 1 |
| Synthetic ID Detection | $27 | Week 2 |
| Cross-Artifact Correlation | $0 | Week 3 |
| Polish & Investor Prep | $0 | Week 4 |
| TOTAL | $81 | 20 Days |

## Final Deliverables

Working KYCShield Middleware API

• Video deepfake detection (95%+ accuracy)

• Synthetic ID detection (95%+ accuracy)

• Cross-artifact correlation

• Real-time analysis (< 1 second)

• RESTful API integration

Enhanced Trusi Consumer App

• Video deepfake detection feature

• Proof of technology for investors

Live Investor Demo

• ProKYC attack demonstration

• Side-by-side comparison

• Real-time detection showcase

Sales & Pitch Materials

• Pitch deck

• ROI calculator

• Integration guide

• Technical documentation

# TECHNICAL SPECIFICATIONS

## Performance Targets

| Metric | Target |
| --- | --- |
| Video Deepfake Detection Accuracy | ≥ 95% |
| ID Synthetic Detection Accuracy | ≥ 95% |
| False Positive Rate | < 1% |
| Video Analysis Speed | < 1 second |
| Document Analysis Speed | < 5 seconds |
| Total Verification Time | < 6 seconds |
| Concurrent Verifications | 1,000+ per hour |

## Detection Capabilities

Video Deepfake Detection:

Detects ProKYC and similar tools

Identifies GAN artifacts, temporal inconsistencies

Catches face-swap and animation attacks

Synthetic ID Detection:

Detects AI-generated documents

Identifies template forgeries

Catches photo manipulation

Cross-Artifact Analysis:

Correlates video and ID signatures

Detects bundled synthetic identities

Identifies coordinated AI generation

# MARKET POSITIONING

## Value Proposition

"The cybersecurity solution that detects ProKYC and similar AI-powered fraud tools that bypass traditional KYC systems."

## Target Customers

Cryptocurrency exchanges (highest risk)

Fintech applications (fast onboarding)

Regional banks (compliance needs)

Payment processors

Neobanks and digital banks

## Competitive Advantage

Not replacing KYC - enhancing existing systems

Middleware integration (works with Jumio, Onfido, etc.)

Specifically targets AI-generated fraud

2-week deployment vs 6-12 month implementations

$0.10-0.25 per verification vs $1-5 traditional KYC

## Market Opportunity

Billions in fraud losses annually from synthetic identities

Fastest-growing fraud segment

ProKYC and similar tools evolving monthly

No effective competition in deepfake KYC defense

# INTEGRATION ARCHITECTURE

## How KYCShield Works

KYCShield operates as a security middleware layer that analyzes verification media before it reaches traditional KYC providers.

Standard Flow:

User → Traditional KYC → Bank

With KYCShield:

User → KYCShield Analysis → Traditional KYC → Bank

## Integration Benefits

No changes to existing KYC infrastructure

Works with any KYC provider (Jumio, Onfido, etc.)

Real-time analysis (< 1 second)

Added security layer

2-week deployment timeline

## API Endpoints

POST /api/v1/kyc/verify - Complete verification

POST /api/v1/document/verify - Document check only

POST /api/v1/face/verify - Face matching

POST /api/v1/liveness/detect - Liveness check

POST /api/v1/fraud/score - Fraud analysis

# STRATEGIC DECISION: VOICE DETECTION

## Rationale for Exclusion in MVP

Voice authentication is dominated by Reality Defender (HSBC contract)

Most KYC flows do not require voice verification

Video + ID detection covers 90%+ of ProKYC attack vectors

Faster path to MVP (saves Week 3 complexity)

Can add voice detection post-MVP if customer demand exists

## Future Voice Integration

If customers request voice clone detection, KYCShield can add:

Voice authenticity detection at enrollment

Protection against synthetic voice enrollment

Complementary to Reality Defender (not competitive)

Estimated: 1 week development, $0 cost (pre-trained models)

## Positioning with Reality Defender

"KYCShield detects synthetic media at enrollment. Reality Defender authenticates real identities during ongoing use. We complement each other."

# INVESTOR DEMO FLOW

## Demo 1: Trusi Consumer App (2 minutes)

Show Trusi mobile app

Upload deepfake video

Detection in < 1 second: "NOT AUTHENTIC - Deepfake detected"

Show accuracy metrics: 93% images, 95% video

Message: "Our technology works and consumers use it"

## Demo 2: ProKYC Threat (3 minutes)

Show ProKYC video demonstration

Explain the attack: Fake ID + Deepfake video + Voice clone

Show how traditional KYC approves the fraud

Message: "This is the threat banks face today"

## Demo 3: KYCShield Protection (3 minutes)

Upload ProKYC attack bundle to KYCShield

Show real-time analysis:

• Document: "SYNTHETIC - AI-generated ID detected"

• Video: "DEEPFAKE - Synthetic face detected"

• Face Match: Correlation analysis

• Verdict: "FAIL - Critical fraud detected"

Message: "KYCShield catches what traditional KYC misses"

## Demo 4: Side-by-Side Comparison (2 minutes)

Split screen:

Left: Traditional KYC → "Approved ✓"

Right: KYCShield → "Blocked ✗ - Fraud detected"

Message: "Same attack, different result"

## The Ask (2 minutes)

Market size: Billions in fraud, no competition

Pricing: $0.10-0.25 per verification

Integration: 2 weeks

First customers: Crypto exchanges (immediate need)

Seeking: $[X] for scale

Total Demo Time: 12 minutes

# SUCCESS CRITERIA

## Technical Milestones

✓ Video deepfake detector: 95%+ accuracy, <1 sec inference

✓ Synthetic ID detector: 95%+ accuracy, <5 sec inference

✓ Cross-artifact correlation: Working algorithm

✓ False positive rate: <1% across all components

✓ Integrated with Trusi mobile app

✓ RESTful API deployed and documented

## Demo Readiness

✓ Live KYCShield demo interface

✓ Recorded demo videos

✓ ProKYC attack demonstration

✓ Side-by-side comparison ready

✓ Demo script practiced and polished

## Sales Materials

✓ Investor pitch deck (15 slides)

✓ ROI calculator

✓ Integration guide

✓ Technical documentation

✓ Threat intelligence brief

## Investor Meeting Readiness

✓ Pitch rehearsed and refined

✓ Q&A preparation complete

✓ Demo runs smoothly (no technical issues)

✓ Messaging clear and compelling

✓ Ready for first week of December meetings

# RISKS & MITIGATION STRATEGIES

## Technical Risks

Risk: Training doesn't achieve 95% accuracy

Mitigation:

• Use proven architectures (3D CNN, ResNet-50)

• Leverage academic datasets with known benchmarks

• Adjust hyperparameters and training duration as needed

• 85%+ accuracy still valuable for MVP demo

Risk: Inference speed too slow

Mitigation:

• Use model optimization techniques

• Deploy on GPU infrastructure

• Parallel processing of video frames

• <2 seconds still acceptable for demo

## Timeline Risks

Risk: Training takes longer than expected

Mitigation:

• Start video training immediately (Week 1)

• Use pre-trained base models to reduce training time

• Parallelize work where possible

• Buffer time built into Week 4

Risk: Dataset acquisition delays

Mitigation:

• Multiple dataset sources identified

• Academic datasets have fast download

• Can generate synthetic data if needed

## Market Risks

Risk: Investors don't understand the threat

Mitigation:

• ProKYC video demonstrates threat clearly

• Prepare threat intelligence brief

• Show real fraud statistics

• Trusi app proves technology works

Risk: Competition emerges

Mitigation:

• First-mover advantage in deepfake KYC defense

• Unique positioning (middleware, not replacement)

• Working product vs. competitors still in development

# PROJECT RESOURCES

## Development Environment

Backend: FastAPI + Python 3.13.7

Database: PostgreSQL (Docker)

Training: Lambda Labs GPU infrastructure

Version Control: GitHub (thkcyberai/facti-ai)

Documentation: /c/python/facti-ai/Docs/

## Training Datasets

Video: FaceForensics++, Celeb-DF, DFDC

Documents: MIDV-500, MIDV-2019, synthetic generation

## Key Technologies

DeepFace (Facenet512) - Face matching

3D CNN - Video deepfake detection

ResNet-50 - Document synthetic detection

OpenCV - Image processing

TensorFlow/PyTorch - Model training

## Related Products

Trusi.ai - Consumer deepfake detection app

Integration: Shares video deepfake detector with KYCShield

END OF TIMELINE

This document outlines the complete 20-day development timeline for KYCShield MVP, targeting investor readiness by first week of December 2025.